## Sheet1
Project | thuc-tap-cnpm | Reporter | Bùi Thế An | Class | MT09KH01
Date | Project Task | Product | WorkType | Unit | ES | AS | Status | EE (h) | AE(h) | LnCo | BrCo | Bug | Note
2012-11-03 | Tìm và tải Python IDE | [5 empty] | Đã hoàn thành | 0.5 | 1
2012-11-03 | Tìm ebook về Python | [5 empty] | đã hoàn thành | 0.25 | 0.5
2012-12-03 | tìm hiểu cách biên dịch từ Python IDE | [5 empty] | đã hoàn thành | 0.25 | 0.1
2012-12-03 | đọc chương 1 và làm bài 1 | folder 50900003 code và file word báo cáo |  |  |  |  | Đã hoàn thành | 1 | 1 | 17 | 3 | 2 | lỗi font chữ do copy paste
13/3/2012 | đọc chương 2 và làm bài 2 | [5 empty] | đã hoàn thành | 1 | 1 | 9 |  |  | xuất không đúng yêu cầu đề bài
14/3/2012 | đọc chương 3 4 | [5 empty] | Đã hoàn thành | 1.5 | 2
15/3/2012 | làm bài 3 | [5 empty] | Đã hoàn thành | 1 | 0.5 | 13 |  |  | không hiểu vì sao vòng lặp ko chạy, xóa làm lại thì chạy
16/3/2012 | làm bài 4 | [5 empty] | đã hoàn thành | 1 | 1.5 |  |  |  | chuong trinh chay khong on dinh, khong biet cach khac phuc
17/3/2012 | viet thu vien bai5_1 | [5 empty] | Đã hoàn thành | 0.5 | 0.25 | 23
17/3/2012 | viet bai5_2 | [5 empty] | Đã hoàn thành | 0.5 | 0.25 | 15
Note on B3: Task in project schedule
Note on F3: Estimated Size
Note on G3: Actual Size
Note on I3: Estimated Effort (hours)
Note on J3: Actual Effort (hours)
Note on K3: Line coverage in Unit Test
Note on L3: Branch coverage in Unit Test
Note on M3: Found bug